## Tasks
Index | Task Type | Tasks | Task Owner | Task Deadline | Dependency | Dependency Owner | Status | Notes
1 | Prework | One Cloud dummy system ID creation | Gao, Kuan | WW02.2 | Anil's approval |  | Done
1 | Prework | Test BAT | Gao, Kuan | WW02.2 |  |  | Done | Remote testing by US team
1 | Prework | 扭力扳手的扭力 | Gao, Kuan |  |  |  | Done | 7 in/Lb = 80 cNm
1 | Prework | GNR AP CPU installation training | Ian | WW02 | Get a trainer from DE | Yang, Vincent | Done
1 | Prework | Pre-kitting | Lin, Wenyan |  | Define qty per type | Ian | Done | Qty = 30
1 | Prework | USB hub connectivity issue | Ren, Xiangzhen |  |  |  | Cancel | Connect Y2Prog to NUC, PDU or NUC power cycle. Status report from Ren, Xiangzhen
1 | Prework | Enable ASD | Tech Leads | WW02 | ASD BKM | Tian, Menghan | Done
1 | Prework | Jumper for BNC 提前拨好 | Tech Leads | WW02 | Jumper name for BNC RP/Modular boards | Tian, Menghan | Done
1 | Prework | Jumper J3A4/J3A5 for AVC 提前拨好 | Tech Leads | WW02 |  |  | Done
1 | Prework | Pre-build USB relay | Tech Leads | WW02 |  |  | Open
1 | Prework | Instrumentation per form factor | Tian, Menghan |  |  |  | Done | Share on WW01.4
1 | Prework | Pre-build KVM | Zhang, Yan |  |  |  | Done
1 | Prework | Pre-build PDU | Zhang, Yan |  | Audit PDU configuration per BKM | Tian, Menghan | Done
1 | Prework | Pre-build NUC | Zhu, Yuanyuan |  |  |  | Done | NUC's are placed to the PID lab benches
2 | PID Lab | Update 5x GNR One Cloud System ID |  | WW02.2 |  |  | Cancel | Downtime is required
2 | PID Lab | PDU理线 | Guo, Linlin/Cheng, Xun |  | 包线管 |  | Open | follow after network cabling completion
2 | PID Lab | 大理线 | Guo, Linlin/Cheng, Xun |  | 包线管 |  | Open | Completed Type-B 21x benches (total 24) and 6x type-A shelves (total 11)
2 | PID Lab | Repair BIOS header pin | Rework Team |  |  |  | Done
2 | PID Lab | Assemble 10x BNC POK (no M.2, no ITP) | Tech Leads | WW02 | POK, Board availability |  | Pending
2 | PID Lab | Assemble 20x BNC CC (no M.2, no ITP) | Tech Leads | WW02 |  |  | Done | Hu, Chengming and Cao, Yuan completed 20 units
2 | PID Lab | Bring up 13x AVC POK w/ VIS Si | Tech Leads | WW06 |  |  | Done
2 | PID Lab | Enable 5x GNR relay, ASD, etc | Tech Leads | WW02.4 |  |  | Cancel
2 | PID Lab | Update floor map and tracker | Tech Leads | WW02 |  |  | Done
2 | PID Lab | Network port issue | Yang, Vincent |  |  |  | Open | Escalated to IT for fix. Must be fixed and tested before CNY, IT POC He, Binjie | Zhang, Xiong to check IT n/w cabling
2 | PID Lab | Network cable re-labeling | Zhang, Xiong | WW01.2 |  |  | Done
2 | PID Lab | PDU outlet naming | Zhang, Yan |  | Naming convension rules | Tian, Menghan | Open
| PID Lab | Fit 2x HSIO full config POK's on one bench | Ian Liu | WW06.5 |  |  | Open
3 | Open Lab | Free up racks occupied by PAIV | Yang, Vincent | WW02.1 |  |  | Closed
3 | Open Lab | 安装 5486 PDU | Zhang, Xiong | WW02.2 |  |  | Closed | Move 5486 PDU to open lab, plan to install on WW02.2
3 | Open Lab | 5482 PDU 上电 | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW02.1 |  |  | Done | Completed for empty racks/benches
3 | Open Lab | 5486 PDU 上电 | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW02.2 |  |  | Done | All racks
3 | Open Lab | Install 5205 PDU 上电 | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW02.1 |  |  | Open | Completed all benches and racks except B01-B04 (outlets are used by PAIV systems)
3 | Open Lab | Rack 贴SUT Name标签 | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW01.4 |  |  | Done | Shutdown air condition
3 | Open Lab | 安装Network cables | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW02.4 |  |  | Open | To be completed on WW02.4 except for B01-B04 (ports are used by PAIV systems)
| Open Lab | Record PDU serial numbers | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW02.5 |  |  | Done | Next step to generate client ID and DDI registration
| Open Lab | 大理线 | Zhang, Xiong/Wu, Yunpeng/Zhou, Yulin/Zeng, Yongjun/Sheng, Yi | WW03 |  |  | Open
4 | Purchase | Debug room and tools | Yang, Vincent |  |  |  | Open | SHZ1 2F Debug Room
4 | Purchase | 吊牌，网线标签纸 | Yang, Vincent |  |  |  | Open
4 | Purchase | 扭力扳手的刀头 | Yang, Vincent |  | Picture and shopping link, 5 | Ren, Xiangzhen | Open | https://item.jd.com/10065888110412.html#crumb-wrap
| Purchase | Air blowing ball | Yang, Vincent |  |  |  | Open

## Open
Date | Open | From | Owner | Status
WW01.3 | 26 Idaville packing material in mini cluster lab inside outside and SHZ1 landing platform, move to SHZ1 1F landing platform 6333 janitor phone | Ju, Yujing |  | Closed
WW01.3 | SHZ1 asset management access rejects Vincent will approve | Ju, Yujing
WW01.3 | barcode scanner, trolley - scanner arrived 3, Vincet will give one trolley | Ju, Yujing
WW01.3 | 35 BNC boards, 10 BNC boards, ITP, NUC, SHZ2 3F short of space | Ju, Yujing |  | Closed
WW01.3 | PO/PPO CPU Jumper for BNC RP/Moduler boards | Ren, Xiangzhen | Tian, Menghan | Closed
WW01.4 | Missing USB relay jumper cables | Ren, Xiangzhen |  | Closed
WW01.4 | Some NUC's are not configured for auto start mode | Ren, Xiangzhen |  | Closed
WW01.4 | Missing some network cables for open lab L12 | Zhang, Xiong |  | Closed
WW01.5 | Receiving 1300+ AIC. Need to compare the expected qty vs the received qty. Physically grouping them by device type with visible labels in the inventory room | Ian | Lin, Wenyan | Closed
WW02.1 | Readiness update by tech leads - WW02.1 | Ian | Tech Leads | Closed
WW02.2 | Torque 7 Lb convert to 80 cNm GNR AP can boot | Zhu, Yuanyuan |  | Closed
WW02.2 | Code B7 seen when 8x DIMM installed, wait 5 minutes before entering BIOS | Zhu, Yuanyuan |  | Closed
WW02.2 | BMC flash failure, solution is to use BIOS Y2Prog | Zhu, Yuanyuan |  | Closed
WW02.2 | Both Y2Prog connected, failed to flash BMC, BMC can be detected | Zhang, Yan |  | Closed
WW02.2 | Short of 5 rack shelves, get 6 pcs from external store | Zhang, Xiong |  | Closed
WW02.2 | Help needed from PAIV | Yang, Vincent |  | Closed
WW02.2 | Thanks Yunpeng and Yulin for fixing a BIOS header pin | Zhu, Yuanyuan |  | Closed
WW02.3 | Lin Yan and Xu, Michael have CPU and DIMM mapping sheet | Yang, Vincent |  | Closed
WW02.3 | HSIO machine PythonSV fail to unlock, provide host names to Kuan, check unlock registration status, currently 2-3 NUC's with the problem, waiting for BAT testing which will also unlock PythonSV | Ren, Xiangzhen | Gao, Kuan | Closed
WW02.3 | CPU heatsink 固定框架，收集， | Ren, Xiangzhen | Tech Leads | Closed
WW02.3 | CPU heatsink 固定框架 统计数量 | Ren, Xiangzhen | Lin, Wenyan | Closed
WW02.3 | HSIO system need more space for peripherals, Vincent will talk to Nessia | Ren, Xiangzhen | Yang, Vincent
WW02.3 | 静电带到货 | Yang, Vincent |  | Closed
WW02.5 | Get compound paste from DE | Ren, Xiangzhen | Zhou, Yulin/Wu, Yunpeng | Closed | 12.8g x3, 1.5g per CPU
WW02.5 | Training to use compound paster | Yang, Vincent | Yang, Vincent | Closed | 1/28 afternoon training
WW02.5 | Backup for Zhu, Yuanyuan and Zhang, Yan between 1/28 and 1/30 | Ian |  | Closed
WW02.5 | One Type A shelf size is small | Guo, Linlin | Yang, Vincent
WW03.2 | Check with US team the CPU compount paste amount needed per CPU | Yang, Vincent | Tian, Menghan | Closed
WW03.2 | Prefer debug space on SHZ1 4F PID lab | Ren, Xiangzhen | Yang, Vincent
WW03.3 | SUT's and instruments are connected to correct PDU sockets per power mapping in the rack design spec | Zhang, Yan | Tian, Menghan | DONE
WW03.3 | add new PDU accounts | Gao, Kuan | Zhang, Yan | DONE
WW03.3 | ITP and NUC are not connected to right PDU sockets, fixed for all installed systems | Gao, Kuan | Sheng, Yi | Closed
WW03.3 | Lin Wenyan ownes consumable material checkin and checkout | Ju, Yujing |  | Closed
WW03.3 | Inventory tracking for consumable materials to be updated by Lin Wenyan and Gu Qiangguang |  | Ian Liu
WW03.3 | Process for debugging faulty materials | Ren, Xiangzhen | Ian Liu
WW03.3 | NUC reconfiguration |  | Hu, Chengming | Closed
WW03.4 | Share the learning from LOM installation error to all technicians |  | Tech Leads | DONE
WW03.4 | Check LOM installation for all installed systems |  | Tech Leads | Closed
WW03.4 | BAT training for technician team after CNY |  | Gao, Kuan | DONE
WW03.4 | Rework for PPO boards, check w/ Zhang, Luming and Lai, Caifu for BKM |  | Ian Liu | Cancel
WW03.4 | Implement 4 eye check |  | Tech Leads | DONE
WW03.4 | Ask Zhang, Luming and Lai, Caifu anything could damage a board |  | Ian Liu | DONE
WW03.4 | More space needed for systems with HSBP |  | Ian Liu | DONE
WW04.6 | Help team to get familiar with AVC board rework PO phase Bulletin#6a | Ian Liu | Tian, Menghan | Cancel
WW04.6 | Confirm if jumper J9A6 for AVC is required or not. What's the jumper for BNC. | Ren, Xiangzhen | Kuan/Menghan
WW05.1 | Borrow 2x GNR AP heatsinks | Zhang, Yan | Yang, Vincent | DONE
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cannot ping 60x PDU becaue PDU power are disconnected. Guo Linlin will connect PDU power.

## Network Port Issue
Location | IP | Status
Z1-04-047 071C (row5 rack2 sut4 NUC) |  | N | no cable connected
ZZ14147007S0502 Z1-04-047-89 ETH/NUC |  | Y | cable connected | Gao, Kuan
Z1-01-047-61 | 10.112.122.134 | Y
Z1-01-047-75 | 10.112.122.164 | Y
Z1-04-047 | 10.112.122.175 | Y
Z1-01-047-6E/201A | 10.112.122.205 | Y
Z1-01-047-72 (BD) | 10.112.122.208 | N
Z1-01-047-6E/026A | 10.112.122.226 | Y
Z1-04-047-149 | 10.112.98.233 | Y
Z1-04-047-156 | 10.112.98.234 | Y
Z1-01-047-6E/151A | 10.112.98.246 | Y
z1-04-047-6E 182B | 10.112.98.81 | Y
z1-04-047-6E 070A | 10.112.98.82 | Y
z1-04-047-6E 193C | 10.112.98.106 |  | Duplicated port name
z1-04-047-6E 193C | 10.112.98.128 | Y
z1-04-047 039B | 10.112.98.143 | Y
z1-04-047-6E 212A | 10.112.98.144 | Y
z1-04-047-6E 209D | 10.112.98.148 | Y | Fixed
z1-04-047-106-C | 10.112.98.170 | Y
z1-04-047-6E 214D | 10.112.98.175 | Y
z1-04-047-6E 223A | 10.112.98.226 | Y
z1-04-047-6E 223B | 10.112.98.228 | Y
z1-01-047-70 A | 10.112.122.174 | Y

## VV Bring Up Plan
Config Identifier | System ID | QDF | CPU QTY | Description | HSD-ES | Chassis | Chassis Change | Chassis QTY | DIMM | DIMM QTY | CXL.MEM | IO | Storage | Status | Tech Lead | Peripheral Status | Full HW Config Complete | Build Short | ETA | BAT | BAT Status | BAT Complete | Comment
SH001 | zz14l47007s0601 | Q2TJ | 2 | MEM CfgX only | 14018007174 | POK | POK | 1 | RE32 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW02.2 | 22016525803 | Release w/ BAT | 1
SH002 | zz14l47005s0103 | Q2V4 | 2 | MEM CfgX only | 14018007174 | CC | CC | 1 | RE32 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW03.2 | 16019582783 | Release w/ BAT | 1
SH003 | zz14l47005s0402 | Q2TK | 2 | MEM CfgX Only | 14018007174 | CC | CC | 1 | RE32 | 8 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW03.2 | 15012707700 | Release w/ BAT | 1
SH004 | zz14l47005s0303 | Q2TK | 2 | MEM CfgX only | 14018007174 | CC | CC | 1 | RE32 | 8 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW05.0 | 15012717519 | Release w/ BAT | 0 | PXE slowness issue
SH005 | zz14l47005s0104 | Q2TM | 2 | MEM CfgX only | 14018007174 | CC | CC | 1 | RE32 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW03.2 | 16019588183 | Release w/ BAT | 1
SH006 | zz14l47007s0503 | Q2TK | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016191525 | POK | POK | 1 | RE32 | 8 |  | 1x CMV 100GbE 1x CMV 100GbE OCP |  | PO | Ren, Xiangzhen | Full Config OK | 1 |  | WW03.2 | 16019587024 | Release w/ BAT | 1
SH007 | zz14l47007s0103 | Q2V4 | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016191525 | POK | POK | 1 | RE32 | 8 |  | 2x CMV 200GbE |  | PO | Zhang, Yan | IO OK | 1 |  | WW05.5 | 15012735404 | Release w/ BAT | 1 | run out of RE32, use RA64
SH008 | zz14l47001s0802 | Q2U2 | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016191525 | POK | POK | 1 | RE32 | 8 |  | 2x CNV 200GbE |  | PO | Zhu, Yuanyuan |  | 1 | 1 | WW05.5 | 15012727122 | Release w/ BAT | 1 | run out of RE32, use RA64
SH009 |  | Q2V4 | 2 | MEM CfgX + 1x RPB + 1x Storage | 22016191635 | CC | POK to CC | 1 | RE32 | 8 |  | 1x RPB | 1x Gen4 U.2 | 1 Q2V4 Faulty | Zhang, Yan |  |  |  | WW06.5 |  |  | 0 | post code FF, 00, 1x CPU is tested faulty with test BIOS
SH010 | zz14l47007s0603 | Q2V4 | 2 | MEM CfgX + 1x RPB + 1x Storage | 22016191635 | POK | POK | 1 | RE32 | 8 |  | 1x RPB | 1x Gen5 U.2 | PO | Zhang, Yan | Storage OK | 1 | 1 | WW05.1 | 15012674577 | Release w/ BAT | 1
SH011 | zz14l47007s0602 | Q2TK | 2 | MEM CfgX only | 22016258588 | POK | POK | 1 | RC32 | 8 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW02.2 | 15012687145 | Release w/ BAT | 1
SH012 | zz14l47005s0301 | Q2TJ | 2 | MEM CfgX only | 22016258588 | CC | CC | 1 | RC32 | 8 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW03.2 | 15012737693 | Release w/ BAT | 0 | Lend to SRE
SH013 | zz14l47007s0202 | Q2TJ | 2 | MEM CfgX only | 22016258588 | POK | POK | 1 | RC32 | 8 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW05.1 | 15012727186 | Release w/ BAT | 1
SH014 | zz14l47007s0203 | Q2TK | 2 | MEM CfgX only | 22016258588 | POK | POK | 1 | RC32 | 8 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW05.1 | 15012789845 | Release w/ BAT | 0
SH015 | zz14l47008s0201 | Q2U2 | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016258589 | POK | POK | 1 | RC32 | 8 |  | 2x CMV 200GbE |  | PO | Zhu, Yuanyuan | Full Config OK | 1 |  | WW05.2 | 15012719606 | Release w/ BAT | 1 | move to row 1
SH016 | zz14l47007s0101 | Q2TK | 2 | MEM CfgX + 2x Intel AIC + 0x Storage |  | POK | POK | 1 | RC32 | 8 |  | 1x CMV 25GbE 1x CMV 25GbE OCP |  | PO | Zhang, Yan | IO OK | 1 |  | WW05.2 | 15012719412 | Release w/ BAT | 1
SH017 | zz14l47007s0102 | Q2TJ | 2 | MEM CfgX only | 14018007174 | POK | POK | 1 | RE32 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW05.1 | 15012719358 | Release w/ BAT | 1
SH018 | zz14l47003s0802 | Q2V4 | 2 | HSIO full IO cfg |  | POK | POK | 1 | RC32 | 8 |  | MIX | MIX | PO | Ren, Xiangzhen |  |  |  | WW02.3 | 15012761921 | Release w/ BAT | 1 | 2/10: passed mem only BAT test
SH019 | zz14l47003s0702 | Q2U2 | 2 | HSIO full IO cfg | 15012621783 | POK | POK | 1 | RC32 | 8 |  | MIX | MIX | PO | Ren, Xiangzhen |  |  |  | WW03.2 | 15012797425 | Release w/ BAT | 0 | HSIO
SH020 | zz14l47007s0303 | Q2U4 | 2 | MEM CfgX only | 22016258631 | POK | POK | 1 | RA64 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW02.3 | 15012706438 | Release w/ BAT | 1
SH021 | zz14l47007s0403 | Q2TK | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016258632 | POK | POK | 1 | RA64 | 8 |  | 1x CMV 100GbE 1x CMV 100GbE OCP |  | PO | Zhu, Yuanyuan | Full Config OK | 1 |  | WW02.3 | 15012684154 | Release w/ BAT | 1
SH022 | zz14l47008s0302 | Q2TK | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016258632 | POK | POK | 1 | RA64 | 8 |  | 2x CNV 25GbE |  | PO | Ren, Xiangzhen |  | 1 | 1 | WW05.2 | 15012726932 | Release w/ BAT | 1
SH023 | zz14l47004s0706 | Q2TH | 2 | MEM CfgX + 2x Intel AIC + 2x Storage | 22016258634 | CC | POK to CC | 1 | RA64 | 8 |  | 2x CNV 25GbE --> 2x CMV 100GbE | 2x Gen5 U.2 | PO | Ren, Xiangzhen | Storage OK | 1 | 1 | WW05.4 | 15012736224 | Release w/ BAT | 1
SH024 | zz14l47004s0601 | Q2U4 | 2 | MEM CfgX + 2x Intel AIC + 2x Storage | 22016258634 | CC | POK to CC | 1 | RA64 | 8 |  | 2x MT.Evans | 1x Gen4 U.2 1x Gen5 U.2 | PO w/ test BIOS | Zhang, Yan |  |  |  |  | 15012786806 | Passed BAT | 0 | 2x Q2U4 faulty CPU's can boot with test BIOS
SH025 | zz14l47007s0502 | Q2TH | 2 | MEM CfgX + 2x Intel AIC + 2x Storage | 22016258634 | POK | POK | 1 | RA64 | 8 |  | 1x CMV 25GbE 1x CMV 25GbE OCP | 2x Gen4 U.2 | PO | Zhu, Yuanyuan | Full Config OK | 1 |  | WW02.4 | 15012659173 | Release w/ BAT | 1
SH026 | zz14l47004s0103 | Q2TH | 2 | MEM CfgX + 2x Intel AIC + 2x Storage | 22016258634 | CC | POK to CC | 1 | RA64 | 8 |  | 1x CMV 25GbE 1x CMV 100GbE OCP | 2x Gen4 U.2 | PO | Zhang, Yan | Full Config OK | 1 |  | WW05.5 | 15012738497 | Release w/ BAT | 1 | Repaired by replacing a CC. Troubleshoot fan slowess issue on the old CC later
SH027 | zz14l47001s0701 | Q2TJ | 2 | MEM CfgX only | 14018007174 | POK | POK | 1 | RE32 | 8 |  |  |  | 2 Q2TJ faulty | Zhu, Yuanyuan | N/A |  |  | WW05.4 | 15012792045 | Passed BAT | 0 | run out of RE32, use RA64 | 2 Q2TJ can boot with test BIOS, need to use a POK board
SH028 | zz14l47005s0302 | Q2TJ | 2 | MEM CfgX only | 14018007174 | CC | CC | 1 | RE32 | 8 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW05.0 | 16019580825 | Release w/ BAT | 1
SH029 | zz14l47008s0202 | Q2TJ | 2 | MEM CfgX only | 22016258588 | POK | POK | 1 | RC32 | 8 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW05.1 | 15012719418 | Release w/ BAT | 1 | move to row 1
SH030 | zz14l47008s0203 | Q2TM | 2 | MEM CfgX only | 22016258588 | POK | POK | 1 | RC32 | 8 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW05.1 | 15012719382 | Release w/ BAT | 1 | move to row 1
SH031 | zz14l47005s0203 | Q2TJ | 2 | MEM CfgX only | 22016258588 | CC | CC | 1 | RC32 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW05.0 | 16019588182 | Release w/ BAT | 1
SH032 | zz14l47005s0204 | Q2TL | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016258589 | CC | CC | 1 | RC32 | 8 |  | 1x CMV 100GbE 1x CMV 100GbE OCP |  | PO w/ test BIOS | Zhu, Yuanyuan | Removed 2x CMV |  |  | WW06 | 15012781503 | Passed BAT | 0 | CPU UPI Issue | Test 2 Q2TL with test BIOS Booted up with test BIOS without CMV, failed if install CMV
SH033 | zz14l47005s0401 | Q2TH | 2 | MEM CfgX + 2x Intel AIC + 2x Storage | 22016258591 | CC | CC | 1 | RC32 | 8 |  | 2x MT.Evans | 1x Gen4 U.2 1x Gen5 U.2 | PO | Zhu, Yuanyuan | Storage OK | 1 | 1 | WW05.0 | 15012712990 | Release w/ BAT | 1
SH034 | zz14l47004s0203 | Q2TJ | 2 | MEM CfgX only | 22016258631 | CC | POK to CC | 1 | RA64 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW05.4 | 15012726967 | Release w/ BAT | 1
SH035 | zz14l47004s0306 | Q2TJ | 2 | MEM CfgX only | 22016258631 | CC | POK to CC | 1 | RA64 | 8 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW05.4 | 15012731361 | Release w/ BAT | 1
SH036 | zz14l47004s1203 | Q2TL | 2 | MEM CfgX only | 22016258631 | CC | POK to CC | 1 | RA64 | 8 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW05.5 | 15012735897 | Release w/ BAT | 1
SH037 | zz14l47005s0403 | Q2TM | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016258632 | CC | CC | 1 | RA64 | 8 |  | 2x CNV 200GbE |  | PO | Zhu, Yuanyuan |  | 1 | 1 | WW05.0 | 15012728128 | Release w/ BAT | 1 | Lend to SRE
SH038 | zz14l47004s0803 | Q2TM | 2 | MEM CfgX + 2x Intel AIC + 0x Storage | 22016258632 | CC | CC | 1 | RA64 | 8 |  | 1x CNV 100GbE 1x CNV 100GbE OCP |  | PO | Ren, Xiangzhen |  | 1 | 1 | WW05.5 | 15012735831 | Release w/ BAT | 1
SH039 | zz14l47004s0903 | Q2TM | 2 | MEM CfgX + 1x RPB + 1x Storage | 22016258633 | CC | POK to CC | 1 | RA64 | 8 |  | 1x RPB | 1x Gen5 U.2 | PO | Ren, Xiangzhen | Storage OK | 1 | 1 | WW06.0 | 15012748402 | Release w/ BAT | 1 | Testing BAT w/ CenOS
SH040 | zz14l47004s1106 | Q2U2 | 2 | MEM CfgX + 2x 3rd party AIC + 2x Storage | 22016258635 | CC | CC | 1 | RA64 | 8 |  | 1x MLNX CX7 1x MLNX CX7 OCP | 2x Gen5 U.2 | 2 Q2U2 faulty | Ren, Xiangzhen |  |  |  | WW06.5 |  |  | 0 | Faulty CPU
SH041 | zz14l47004s0102 | Q2TH | 2 | MEM CfgX + 6x MIX AIC + 8x Storage | 22016258637 | POK | POK | 1 | RA64 | 8 |  | 1x CMV 100GbE 1x CMV 25GbE OCP 2x CNV 25GbE 1x MT.Evans 1x MLNX CX6 | 4x Gen4 U.2 4x Gen5 U.2 | PO | Zhu, Yuanyuan | Partial IO OK, Storage OK | 1 | 1 | WW05.2 | 15012719428 | Release w/ BAT | 1 | space constraint
SH042 | zz14l47004s0202 | Q2V4 | 2 | MEM CfgX + 1x Intel AIC + 2x Storage | 22016467711 | POK | POK | 1 | RA64 | 8 | 8x CA64 | 1x CMV 25GbE | 2x Gen4 U.2 | PO | Zhang, Yan |  | 1 | 1 | WW05.2 | 15012790224 | Release w/ BAT | 0
SH043 | zz14l47004s0305 | Q2V4 | 2 | MEM CfgX + 1x Intel AIC + 2x Storage | 22016467711 | POK | POK | 1 | RA64 | 8 | 8x CA64 | 1x CNV 25GbE | 2x Gen5 U.2 | PO | Zhang, Yan | Storage OK | 1 | 1 | WW05.2 | 15012719574 | Release w/ BAT | 1
SH044 | zz14l47004s0402 | Q2TP | 2 | MEM CfgX + 1x 3rd party AIC + 2x Storage | 22016467712 | POK | POK | 1 | RA64 | 8 | 8x CA64 | 1x MLNX CX6 | 2x Gen4 U.2 | PO | Ren, Xiangzhen | IO OK, Storage OK | 1 | 1 | WW05.2 | 15012727144 | Release w/ BAT | 1
SH046 | zz14l47004s0602 | Q2TK | 2 | MEM CfgX + 1x Intel AIC + 2x Storage | 22016467715 | POK | POK | 1 | RA64 | 8 | 4x CB128 | 1x CNV 25GbE | 2x Gen5 U.2 | PO | Ren, Xiangzhen | Storage OK | 1 | 1 | WW05.4 | 15012727079 | Release w/ BAT | 1
SH047 | zz14l47004s0705 | Q2TK | 2 | MEM CfgX + 1x Intel AIC + 2x Storage | 22016467715 | POK | POK | 1 | RA64 | 8 | 4x CB128 | 1x MT.Evans | 2x Gen5 U.2 | PO | Ren, Xiangzhen | Storage OK | 1 | 1 | WW05.4 | 15012727238 | Release w/ BAT | 1
SH045 | zz14l47004s0502 | Q2TJ | 2 | MEM CfgX + 1x Intel AIC + 2x Storage | 22016467715 | POK | POK | 1 | RA64 | 8 | 4x CB128 | 1x CMV 25GbE | 2x Gen4 U.2 | PO | Zhu, Yuanyuan | IO OK, Storage OK | 1 | 1 | WW05.2 | 15012719487 | Release w/ BAT | 1 | Use MCIO->CEM cable M58607-002
SH048 | zz14l47004s0802 | Q2TK | 2 | MEM CfgX + 1x 3rd party AIC + 2x Storage | 22016467716 | POK | POK | 1 | RA64 | 8 | 4x CB128 | 1x MLNX CX6 | 2x Gen4 U.2 | 1 Q2TK faulty | Zhu, Yuanyuan |  |  |  | WW05.4 |  |  | 0 |  | CPU cannot boot with test BIOS 彻底坏的CPU
SH049 | zz14l47004s0801 | Q2TN | 1 | MEM CfgX only | 22016491974 | CC | CC | 1 | RC32 | 4 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW06.0 | 15012738488 | Release w/ BAT | 1
SH050 | zz14l47004s0901 | Q2TN | 1 | MEM CfgX only | 22016491974 | CC | CC | 1 | RC32 | 4 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW06.0 | 15012738459 | Release w/ BAT | 1 | DIMM Issue
SH051 | zz14l47004s1001 | Q2TN | 1 | MEM CfgX only | 22016491974 | CC | CC | 1 | RC32 | 4 |  |  |  | PO | Ren, Xiangzhen | N/A | 1 |  | WW06.1 | 15012738476 | Release w/ BAT | 1
SH052 | zz14l47004s1201 | Q2TN | 1 | MEM CfgX only | 22016491974 | CC | CC | 1 | RC32 | 4 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW06.0 | 15012738486 | Release w/ BAT | 1
SH053 | zz14l47004s1003 | Q2TN | 1 | MEM CfgX only | 22016491974 | CC | CC | 1 | RC32 | 4 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW06.0 | 15012738468 | Release w/ BAT | 1
SH054 | zz14l47001s0801 | Q2TN | 1 | MEM CfgX only | 22016491974 | POK | POK | 1 | RC32 | 4 |  |  |  | PO | Zhu, Yuanyuan | N/A | 1 |  | WW06.1 | 15012738503 | Release w/ BAT | 1
SH055 | zz14l47008s0501 | Q2TN | 1 | MEM CfgX only | 22016491974 | POK | POK | 1 | RC32 | 4 |  |  |  | PO | Zhang, Yan | N/A | 1 |  | WW06.0 | 15012738453 | Release w/ BAT | 1
SH056 | zz14l47008s0502 | Q2TN | 1 | MEM CfgX + 1x Intel AIC + 0x Storage | 22016497289 | POK | POK | 1 | RC32 | 4 |  | CMV 25GbE |  | PO | Zhang, Yan | Full Config OK | 1 |  | WW06.0 | 15012738456 | Release w/ BAT | 1
SH057 | zz14l47001s0803 | Q2TN | 1 | MEM CfgX + 1x Intel AIC + 0x Storage | 22016497289 | POK | POK | 1 | RC32 | 4 |  | CMV 25GbE |  | PO | Zhu, Yuanyuan | IO OK | 1 |  | WW06.1 | 14018630482 | Release w/ BAT | 1
|  |  |  | MEM CfgX only | 22016467724 |  |  | 1 | RA64 | 8 |  |  |  | No CPU |  | N/A | [5 empty] | 0
|  |  |  | MEM CfgX only | 22016467724 |  |  | 1 | RA64 | 8 |  |  |  | No CPU |  | N/A | [5 empty] | 0
|  |  |  | MEM CfgX only | 22016467724 |  |  | 1 | RA64 | 8 |  |  |  | No CPU |  | N/A | [5 empty] | 0
|  |  |  | MEM CfgX only | 22016467724 |  |  | 1 | RA64 | 8 |  |  |  | No CPU |  | N/A | [5 empty] | 0
|  |  |  | MEM CfgX only | 22016467724 |  |  | 1 | RA64 | 8 |  |  |  | No CPU |  | N/A | [5 empty] | 0
|  |  |  | MEM CfgX only | 22016467724 |  |  | 1 | RA64 | 8 |  |  |  | No CPU |  | N/A | [5 empty] | 0
SH058 | zz14l47004s0902 | Q2V4 | 2 | MEM CfgX + 6x MIX AIC + 8x Storage | 22016191679 | POK | POK | 1 | RC32 | 8 |  | 2x CMV 200GbE 2x CNV 200GbE 1x MT.Evans 1x MLNX CX6 | 4x Gen4 U.2 4x Gen5 U.2 | PO w/ test BIOS | Zhu, Yuanyuan | Removed 2x CMV and 1x MLNX CX6 |  |  | WW06.2 | 15012781515 | Passed BAT | 0 | 1 CPU severly oxidative | Test 2 Q2V4 with normal/test BIOS 2/10 hang at 55 when normal BIO and CX6, can boot with test BIOS w/o CMV, failed if install CX6
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: upgrade to 22016258652
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Faulty
Note on U48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15012719487

## Resource
|  |  | WW02 |  |  |  |  | WW03 | [5 empty] | WW04 | [6 empty] | WW05
|  |  | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30
|  |  | Mon | Tue | Wed | Thu | Friday | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Zhu, Yuanyuan | Byo | Zhu, Yuanyuan | 2023-01-09: Bringup; 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup
| Byo | Guo Linlin | 2023-01-09: Cabling; 2023-01-10: Cabling; 2023-01-11: Cabling; 2023-01-12: Cabling; 2023-01-13: Cabling; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
| Byo | He Jiale |  | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | [7 empty] | Bringup | Bringup | Bringup
| Byo | Zeng Yongjun | 2023-01-09: L12; 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
| Byo | Hu Chengming | 2023-01-10: BNC CC; 2023-01-11: BNC CC; 2023-01-12: BNC CC; 2023-01-13: BNC CC; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-19: Bringup; 2023-01-20: Bringup
Zhang, Yan | Neu | Zhang Yan | 2023-01-09: Bringup; 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-19: Bringup; 2023-01-20: Bringup; 2023-01-30: Bringup
| Byo | Wen Mengtian | 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-19: Bringup; 2023-01-20: Bringup
| Byo | Chu Xinrong | 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
| Neu | Fan, Mingjian | 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
| Byo | Cheng Xun | 2023-01-09: Cabling; 2023-01-10: Cabling; 2023-01-11: Cabling; 2023-01-12: Cabling; 2023-01-13: Cabling; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
Ren, Xiangzhen | Neu | Ren Xiangzhen | 2023-01-09: Bringup; 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-19: Bringup; 2023-01-20: Bringup; 2023-01-28: Bringup
| Neu | Cao Yuan | 2023-01-10: BNC CC; 2023-01-11: BNC CC; 2023-01-12: BNC CC; 2023-01-13: BNC CC; 2023-01-16: L12; 2023-01-17: L12; 2023-01-18: L12
| Neu | Lei Xiang |  | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | Bringup | [7 empty] | Bringup | Bringup | Bringup
| Neu | Sheng Yi | 2023-01-09: L12; 2023-01-10: L12; 2023-01-11: L12; 2023-01-12: L12; 2023-01-13: L12; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-19: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
| Neu | Zhang Xiong | 2023-01-09: L12; 2023-01-10: L12; 2023-01-11: L12; 2023-01-12: L12; 2023-01-13: L12; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
| Neu | Fei Yuming | 2023-01-10: Bringup; 2023-01-11: Bringup; 2023-01-12: Bringup; 2023-01-13: Bringup; 2023-01-16: Bringup; 2023-01-17: Bringup; 2023-01-18: Bringup; 2023-01-19: Bringup; 2023-01-28: Bringup; 2023-01-29: Bringup; 2023-01-30: Bringup
Rework | Pac | Wu, Yunpeng | 2023-01-09: L12; 2023-01-10: L12; 2023-01-11: L12; 2023-01-12: L12; 2023-01-13: L12; 2023-01-16: Rework; 2023-01-17: L12; 2023-01-18: L12
| Pac | Zhou, Yulin | 2023-01-09: L12; 2023-01-10: L12; 2023-01-11: L12; 2023-01-12: L12; 2023-01-13: L12; 2023-01-16: Rework; 2023-01-17: L12; 2023-01-18: L12; 2023-01-28: Rework; 2023-01-29: Rework; 2023-01-30: Rework
Inventory | Pac | Lin, Wenyan |  | Pre-kitting | Pre-kitting | Pre-kitting | Pre-kitting | Pre-kitting | Pre-kitting | Pre-kitting | Inventory | Inventory | [7 empty] | Inventory | Inventory | Inventory
| Pax | Ju, Yujing | 2023-01-09: Inventory; 2023-01-10: Inventory; 2023-01-11: Inventory; 2023-01-12: Inventory; 2023-01-13: Inventory; 2023-01-16: Inventory; 2023-01-17: Inventory; 2023-01-18: Inventory; 2023-01-28: Inventory; 2023-01-29: Inventory; 2023-01-30: Inventory
[5 empty] | Before | After
|  |  | Zhu, Yuanyuan | Team Lead | He, Jiale | Guo, Linlin
|  |  | Zhang, Yan | Team Lead |  | Chu, Xingrong
CPU Installation |  | Hu, Chengming and Zeng, Yongjun
Fei, Yuming
Wen, Mengtian and Chu, Xinrong
Run BAT |  | Zhang, Xiong
Fan, Mingjian
Zeng, Yongjun
Chu Xinrong
BAT Pre-requisite |  | Lei, Xiang
Zeng, Yongjun
Hu, Chengming
Chu Xinrong

## Sum
Row Labels | Count of Status | Sum of Full HW Config Complete | Sum of BAT Complete | Sum of Build Short
HSIO full IO cfg | 2 |  | 0
MEM CfgX + 1x 3rd party AIC + 2x Storage | 2 | 1 | 1 | 1
MEM CfgX + 1x Intel AIC + 0x Storage | 2 | 1 | 0
MEM CfgX + 1x Intel AIC + 2x Storage | 5 | 4 | 3 | 4
MEM CfgX + 1x RPB + 1x Storage | 3 | 2 | 1 | 2
MEM CfgX + 2x 3rd party AIC + 2x Storage | 1 |  | 0
MEM CfgX + 2x Intel AIC + 0x Storage | 10 | 8 | 7 | 4
MEM CfgX + 2x Intel AIC + 2x Storage | 5 | 3 | 3 | 2
MEM CfgX + 6x MIX AIC + 8x Storage | 2 | 1 | 1 | 1
MEM CfgX only | 32 | 25 | 21
Grand Total | 64 | 45 | 37 | 14

## PN Map
GNR-AP System Config Consolidated Sheet.xlsx |  | Fill out BL , BR-BU by EO
In Stock | Configuration Spec | Configuration Category | Part Number | Part Description
YES | SSDPEK1A118GA01 / 99AGG3 | Boot Drive
YES | CMV 100GbE | IO | E810CQDA2 / 978322 | 2 Port, QSFP28 100/50/25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x16 HHHL
YES | CMV 100GbE OCP | IO | E810CQDA2OCPV3 / 983581 | 2 Port, QSFP28 100/50/25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x16 OCP3.0
YES | CMV 200GbE | IO | E8102CQDA2G1P5 / 99A13V | 2 Port, QSFP28 100/50/25/10GbE, RDMA (iWARP & RoCEv2) (200GbE bifurcated) PCIe Gen4 x16, FHHL
YES | CMV 25GbE | IO | E810XXVDA2 / 978331 | 2 Port, SFP28 25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x8 HHHL
YES | CMV 25GbE OCP | IO | E810XXVDA2OCPV3 / 983262 | 2 Port, SFP28 25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x8 OCP3.0, 5pack
NO | CNV 200GbE | IO
NO | CNV 25GbE | IO
NO | CNV 100GbE
NO | CNV 100GbE OCP
NO | CNV 25GbE OCP
NO | MT.Evans/OSC ADP/LCS (Lancaster Sound)/Rialto Bridge | IO
Shipping | RPB (M47487-002) | IO | M47487-00x | Race Point Beach, CEM FF, FM85 B STEP. Capacity for 2 ‘independent’ Cambria-R / LVF images. NO IDE
YES | RA64 (16Gb 2R X4) | RDIMM | M90109-001 | Samsung DIMM M321R8GA0BB0-CWMAH 2Rx4 5600MBPS 64GB
YES | RC32 (16Gb 1R X4) | RDIMM | M87127-001 | Samsung DIMM M321R4GA0BB0-CWMXH 32GB 1Rx4 PC5-5600B-RC0-1010-XT
YES | RE32 (16Gb 2R X8) | RDIMM | M80836-001 | SK Hynix HMCG88AGBRA191N 32GB 2Rx8 PC5-5600B-RE0-1010-XT
YES | Gen4 U.2 / Gen4 E1.S | Storage | MZQL27T6HBLA-00A07 | Samsung SSD PM9A3 (7680GB, NVMe, 2.5 Inch) Gen4 X4/Single Port
YES | Gen5 U.2 / Gen5 E1.S | Storage | MZWLO1T9HCJR-00B5C | PCIe Gen5x4 / NVMe, PM1743 w/ Elan controller, 2 TB
NO | CA64 | CXL.MEM
NO | CB128 | CXL.MEM
NO | MLNX CX5 | IO
YES | MLNX CX6 | IO | MCX651105A-EDAT | [ConnectX-6] VPI adapter card, 100Gb/s (HDR100, EDR InfiniBand), single-port QSFP56, PCIe4.0 x8
YES | MLNX CX6 | IO | MCX623105AN-VDAT | [ConnectX-6] Dx HHHL single port QSFP56, PCIe Gen 4 x16 (200, 100, 50, 25, 10 GbE speed supported)
YES | MLNX CX6 OCP | IO | MCX631432AN-ADAB | [ConnectX-6] Lx OCP 3.0, dual port SFP28, PCIe Gen 4 x8 (25, 10, 1 GbE speed supported)
YES | MLNX CX7 | IO | MCX75310AAS-NEAT | [ConnectX-7] NDR single port, OSFP, PCIe Gen5x16, HHHL
YES | MLNX CX7 | IO | MCX75310AAS-HEAT | [ConnectX-7] NDR200 single port, OSFP, PCIe Gen5x16, HHHL

## Readiness Checklist (hidden)
Checklist | Ren, Xiangzhen | Zhu, Yuanyuan | Zhang, Yan
Number of System | 4 | 6 | 3
L9 system healthy status | 3 GNR | 1 SPR, 1 GNR (Nessia) | 1 GNR
Instrument readiness Y2Prog, USB Blaster II, XDP, ADC, USB Relay, USB hub, NUC, KVM, BIOS/BMC serial console | No relay jumper cables | 4 relay ready | 2 relay ready
L12 PDU, network readiness (NUC, KVM, ETH, BMC) | OK | OK | check 2 ports
CPU jumper setting for J3A4/J3A5 | OK | OK | WW02 morning
IFWI - BMC, BIOS, CPLD image | Image version | Image version | Image version | AR to Kuan/Menghan
Engineer and role (who do what) - who will install CPU
Tools (5x torque wrench, etc) | OK | OK | OK
USB port COM definition | OK | BMC COM port 230 | OK | AR to Kuan/Menghan
AVC ASD J2A2 (pin 1 and 2) jumper setting | OK | OK | OK
Any other issue | NO | NO | NO
Tool Box
Available boards | 1 | 5 | 2

## PO Checklist
Power On
Run BAT
Enable ASD
Push to One Cloud
Update Floor Map & Tracker
NUC join domain
Tag
RPB
IO
Storage

## HLP
Actual
2023-01-18 | Prepare work bench (space, power, network) |  |  |  | Wu, Yunpeng/Zhou, Yulin
| Prepare Tools, 小理线材料 |  |  |  | Tech Leads
| Download HSD to Sharepoint |  |  |  | Ian Liu
| Record PN# for AVC/BNC POK/Board/CC |  |  |  | Guo, Linlin
DAY1 | Unpack AVC MB/CC (注意: 不要丢任何东西，除了空盒子, Jiang Dianhui检查) |  |  |  | Tech Leads/Jiang, Dianhui
| Place MB/CC to designated bench/shelf location |  |  |  | Guo Linlin
| Collect Host/BMC MAC addresses (Write hostname on box) |  |  |  | Guo Linlin
| Give one board to Chu, Xingrong to replace the BB in SH010 zz14l47007s0603 |  |  |  | Chu, Xingrong
| DDI registration |  |  |  | Gao, Kuan
| Register asset information |  |  |  | Ju Yujing/Lin Wenyan
| Check board TA# |  | No need for TA# M35124-007, PBA# M23789-302 |  | Zhou, Yulin
DAY2 | Check out CPU, DIMM, M.2, Pre-kitting bag from Lin, Wenyan
Bring up SUT
| Update PDU outlet name per naming convension |  |  | do by RASP engineers
| Update One Cloud |  |  | do by RASP engineers
| Run BAT |  |  | do by RASP engineers
BAT Pre-requisite
| NUC | Latest Image installed |  | OK
|  | Joined to domain |  | Gao Kuan will follow up |  |  | SUT1 | SUT2 | SUT3
|  | Logged to lab_raspdcg |  | Login ID |  | 9:00-10:00 | Board, DIMM, LOM, Jumper, CPU
|  | PXE boot disabled |  | Zhu, Yuanyuan will follow up |  | 10:00-11:00 | Flash BKC, QC, Boot
|  | Run ansible pre-BAT |  | N/A |  | 11:00-12:00 | Debug / ITP, Instruments
| BMC | Config BMC |  | add debug user account |  | 12:00-13:00 |  | Lunch
[6 empty] | 13:00-14:00 | Debug / Load OS, VR Rework
[6 empty] | 14:00-15:00 | Update One Cloud
[6 empty] | 2h | Run BAT
[6 empty] | 0.5h | Dinner
[6 empty] | 0.5h | Back to Bench, Bring Online
[6 empty] | 0.5h | Update PDU socket name, Tracker

## Risk
Risk | Mitigation Action | Help Needed from US Team | Anil's Response
Failed to boot up QDF Q2U2 | 1. Reproduced the issue in PAIV lab and found it hang in CpuMpPei driver. PAIV is further debugging. 2. Avoid using Q2U2. Use other QDF’s to bring up systems |  | @Villagran Lopez and @B R, Sridhar lets stay tuned to this and proliferate this info as needed for respective sites.
No knowledge on AIC installation | 1. SH team needs training/assistance on installing the AIC’s (e.g. Gen4 U.2, CMV 100GbE OCP) 2. If AIC uses accessories (e.g. cables, kits), we need the part numbers | 1. Provide AIC installation training/assistance to SH team 2. Provide AIC accessory part numbers to SH team | Will chat with @Villagran Lopez, MaFer and get back to you. We may had this covered in training but if a refresher needs to happen will arrange for it ..
BAT
Material gap for ramping 66x GNR AP 1. DIMM RE32 2. Boot Drive M.2 | Mary and Manuel
HSIO 1. Configuration unclear 2. Rack space constrain
Board damage
PPO rework or 3x VV boards | Liliana
Short of CPU carrier clips
Missing components
Fasten ADC (Plastic boxes or Velcro) | MaFer
HSBP | Liliana and Manuel

## Timeline
|  |  |  | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15
| Total BB | Done | QTY to Build | WW04.6 | WW05.0 | WW05.1 | WW05.2 | WW05.3 | WW05.4 | WW05.5 | WW05.6 | WW06.0 | WW06.1 | WW06.2 | WW06.3 | WW06.4 | WW06.5 | WW06.6 | WW07.0 | WW07.1 | WW07.2 | WW07.3
CC | 30 | 4 | 26 | 2023-01-29: 6; 2023-02-02: 8; 2023-02-03: 9; 2023-02-04: 3
POK PO | 33 | 8 | 25 | 2023-01-30: 6; 2023-01-31: 9; 2023-02-01: 9; 2023-02-02: 1
Release w/ BAT |  | 4 |  | 2023-01-29: 6; 2023-01-30: 6; 2023-01-31: 6; 2023-02-01: 6; 2023-02-02: 6; 2023-02-03: 6; 2023-02-04: 6; 2023-02-05: 6; 2023-02-06: 6; 2023-02-07: 5
[8 empty] | Adjusted Goal |  |  |  | NEW | DEBUG | FAULTY | NO CPU | DAMAGE
[6 empty] | SUT Goal | 23 | 6 | 6 | 6 |  | 10 | 3 | 5 | 6 | 2
[6 empty] | SUT Actual | 23 | 6 | 7 | 3

## CPU Inventory
WW of Request (WW.Day) | Platform Needed for | SOC | Phase/Milestone | Stepping | Production Type | QDF/SKU | Quantity | Requestor Name | Recipient Name | Recipient WWID | Recipient Address | Status | MIR/MRS # | WW Sent | ETA | Tracking | GNR Si Demand Tracking File.xlsx
WW53.2 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2U2 | 2 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 650604 | WW53.3 |  | 4090189364
WW53.2 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TJ | 2 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 650604 | WW53.3 |  | 4090189364
WW53.2 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2V4 | 3 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 650604 | WW53.3 |  | 4090189364
WW53.4 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2V4 | 3 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 651324 | WW53.5 |  | 6772884672
WW53.4 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TK | 6 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 651324 | WW53.5 |  | 6772884672
WW01.2 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TH | 2 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 652220 |  | 2023-01-11 | 7154778875
WW01.2 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2U2 | 2 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 652220 |  | 2023-01-11 | 7154778875
WW01.2 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2U4 | 4 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 652621 |  | 2023-01-10 | 9199403054 | CPU On Hand |  | CPU Defined
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TH | 4 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Row Labels | Sum of Quantity | Row Labels | Sum of CPU QTY
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2U2 | 4 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TH | 10 | Q2TH | 10
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TJ | 4 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TJ | 22 | Q2TJ | 22
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2V4 | 4 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TK | 22 | Q2TK | 22
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TK | 10 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TL | 4 | Q2TL | 4
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TM | 3 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TM | 11 | Q2TM | 10
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TN | 2 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TN | 9 | Q2TN | 9
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TJ | 6 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2TP | 2 | Q2TP | 2
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TM | 8 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2U2 | 9 | Q2U2 | 8
WW01.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TN | 7 | Solorzano Avila, Miriam | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 653604 | WW01.5 | 2023-01-18 | 6911106941 | Q2U4 | 4 | Q2U4 | 4
WW02.1 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TH | 4 | Turner, Gary | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 655772 |  |  | 5403817156 | Q2V4 | 17 | Q2V4 | 14
WW02.1 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TJ | 4 | Turner, Gary | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 655772 |  |  | 5403817156 | Grand Total | 110 | Grand Total | 105
WW02.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2U2 | 1 | Turner, Gary | Liu, Ian | 10590994 | DEG SHZ1 INVENTORY STORE 1F | Received | 655777 |  |  | 1456860786
WW02.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TL | 4 | Turner, Gary | Liu, Ian | 10590995 | DEG SHZ1 INVENTORY STORE 1F | Received | 655777 |  |  | 1456860786
WW02.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2V4 | 4 | Turner, Gary | Liu, Ian | 10590996 | DEG SHZ1 INVENTORY STORE 1F | Received | 655777 |  |  | 1456860786
WW02.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TP | 2 | Turner, Gary | Liu, Ian | 10590997 | DEG SHZ1 INVENTORY STORE 1F | Received | 655777 |  |  | 1456860786
WW02.3 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TJ | 2 | Turner, Gary | Liu, Ian | 10590998 | DEG SHZ1 INVENTORY STORE 1F | Received | 655777 |  |  | 1456860786
WW03.5 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TK | 6 | Turner, Gary | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 659468 |  |  |  |  | 50.5
WW03.5 | BHS-GNR | UCC | Alpha | A1 | VIS | Q2TJ | 4 | Turner, Gary | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 659468
[6 empty] | Q2V4 | 3 | Turner, Gary | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F | Received | 662142
WW06.3 | BHS-GNR | UCC | Alpha | A2 | VIS | Q31F | 1 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F |  | 666924
WW06.3 | BHS-GNR | UCC | Alpha | A2 | VIS | Q31G | 1 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F |  | 666924
WW06.3 | BHS-GNR | UCC | Alpha | A2 | VIS | Q31N | 1 | Mayo, Marion | Liu, Ian | 10590993 | DEG SHZ1 INVENTORY STORE 1F |  | 666924
WW06.3 | BHS-GNR | UCC | Alpha | A2 | VIS | Q31K | 1 | Mayo, Marion | Liu, Ian | 10590994 | DEG SHZ1 INVENTORY STORE 1F |  | 666924
WW07.1 | BHS-GNR | UCC | Alpha | A2 | VIS | Q31M | 6 | Turner, Gary | Liu, Ian | 10590994 | DEG SHZ1 INVENTORY STORE 1F | Shipping | 667305
[6 empty] | Q2HW | 32 |  |  |  | SRF | Received
[6 empty] | Q2HR | 20 |  |  |  | SRF | Received
[6 empty] | Q2HT | 20 |  |  |  | SRF | Received
WW01.4 | BHS-GNR | XCC |  | A1 |  | Q1KD | 5 |  |  |  | GNR SP | Received | CGIRK-16606 | WW01.4 | WW03 | ISM#1305396022

## CPU Balance
CPU QDF | In Stock | Needed | In Use | Faulty | Balance | Stortage
Q2TH | 10 | 10 | 10 |  | 0 | 0
Q2TJ | 22 | 22 | 20 | 2 | 0 | -2
Q2TK | 22 | 22 | 20 | 1 | 1 | -1
Q2TL | 4 | 4 | 2 | 1 | 1 | -1
Q2TM | 11 | 10 | 10 | 1 | 0 | 0
Q2TN | 9 | 9 | 9 |  | 0 | 0
Q2TP | 2 | 2 | 2 |  | 0 | 0
Q2U2 | 9 | 8 | 6 | 2 | 1 | -1
Q2U4 | 4 | 4 | 2 | 2 | 0 | -2
Q2V4 | 17 | 16 | 14 | 1 | 2 | 0
Test BIOS

## AIC Inventory
tab “SH Distribution” |  |  | https://jira.devtools.intel.com/browse/CGIRK-14359
Tracker for systems.xlsx
IHV | IO category | Category Name | Device type | Family | Ordering Info | Description | Intel PO | SH | Shipping | Received
Adaptec | Gen3 PCIE |  | RAID/HBA |  | 2277500-R (8805) | 12 Gbps PCIe Gen3 SAS/SATA RAID Adapter | 3002097965 | 2 | Y | Y
Amphenol | IO debug |  | Test Card |  | HMC38-0515 | MCIO STR to STR 650mm | 3500058683 | 63 | Y | Y
Amphenol | IO debug |  | Test Card |  | HMC38-0210 | MCIO STR to RA 650mm | 3500058683 | 63 | Y | Y
AMD | Gen4 PCIE |  | Discrete Graphics |  | Radeon RX 6800 DT | AMD RX6800 DT dGFX card supporting PCIe Gen4 P3-50122-0003 | 273469 | 1 | Y | Y
Broadcom | Gen3 PCIE / OCP |  | Network/Interconnect |  | BCM957412N4120C | NetXtreme® E-Series Dual-Port 10gbe OCP 3.0 Adapter | 3002092621 | 5 | Y | Y
Broadcom | Gen4 PCIE |  | Network/Interconnect |  | BCM957508-P2100G | Dual-Port 100 Gb/s QSFP56 Ethernet PCI Express 4.0 x16 NIC | 3002092621 3500058685 | 5 | Y | Y
Broadcom | Gen4 PCIE |  | Switch |  | P411W-32P | x16 PCIe Gen 4 Host Interconnect, PCIe NVME switch adapter board | 3002094917 | 3 | Y | Y
Broadcom | Gen5 PCIE |  | Switch |  | P3-50122-00/W1206-600011 | Broadcom G5 Switch Atlas, 144L HIB | 3002093399 | 5
Emulex | Gen3 PCIE |  | Network/Interconnect |  | LPe31002-M6 | Dual Port 16Gb Fibre Channel HBA | 3002094862 | 3 | Y | Y
Emulex | Gen3 PCIE |  | Network/Interconnect |  | LPe32002-M2 | (Lancer G6) dual-port HBA - host bus adapter | 3002094862 | 3 | Y | Y
Emulex | Gen4 PCIE |  | Network/Interconnect |  | LPE35002-M2 | PCI Express 4.0 x8, host bus adapter, FC | 3002094862 | 3 | Y | Y
GIGABYTE | Gen4 PCIE |  | Discrete Graphics |  | GV-N3080GAMING OC-10GD | GeForce RTX 3080 GAMING OC 10G | 3002092211 | 1 | Y | Y
Infineon | IO debug |  | TPM |  | TPM7020XENONBOARDTOBO1 | Infineon TPM2.0 Module, TPM7020XENONBOARDTOBO1 | 3002092210 3500056923 | 8
Intel | Gen3 PCIE |  | Network/Interconnect | Fortville/Carlsville | X710T4 / 943052 | 4 port, 4x10GbE Intel X710.PCIe Gen3 x8, HHHL | 18023577 | 2 | Y | Y
Intel | Gen3 PCIE |  | Network/Interconnect | Fortville/Carlsville | XXV710DA2 / 948651 | 2 port, SFP+ DA, 2x10GbE. PCIe 3 x8, HHHL | 18129965 | 2 | Y
[5 empty] | XXV710DA2TLG1P5 / 999MC7 |  |  |  | Y | Y
Intel | Gen4 PCIE | CMV 25GbE | Network/Interconnect | Columbiaville | E810XXVDA2 / 978331 | 2 Port, SFP28 25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x8 HHHL | 18023578 | 72 | Y | Y
Intel | Gen4 PCIE | CMV 100GbE | Network/Interconnect | Columbiaville | E810CQDA2 / 978322 | 2 Port, QSFP28 100/50/25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x16 HHHL | 18023580 | 90 | Y | Y
Intel | Gen4 PCIE | CMV 200GbE | Network/Interconnect | Columbiaville | E8102CQDA2G1P5 / 99A13V | 2 Port, QSFP28 100/50/25/10GbE, RDMA (iWARP & RoCEv2) (200GbE bifurcated) PCIe Gen4 x16, FHHL | 18023580 | 90 | Y | Y
Intel | Gen4 PCIE | CMV 25GbE | Network/Interconnect | Columbiaville | E810XXVDA4LG1P5 / 979091 | 4 Port, SFP28 25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x16, HHHL | 18023580 18023582 | 72 | Y | Y
Intel | Gen4 PCIE / OCP | CMV 25GbE OCP | Network/Interconnect | Columbiaville | E810XXVDA2OCPV3 / 983262 | 2 Port, SFP28 25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x8 OCP3.0, 5pack | 18023577 | 18 | Y | Y
Intel | Gen4 PCIE / OCP | CMV 100GbE OCP | Network/Interconnect | Columbiaville | E810CQDA2OCPV3 / 983581 | 2 Port, QSFP28 100/50/25/10GbE, RDMA (iWARP & RoCEv2) PCIe Gen4 x16 OCP3.0 | 18023577 18023578 | 18 | Y | Y
Intel | Gen3 PCIE / M.2 |  | OS Storage | OX Creek (P1600x) | SSDPEK1A118GA01 / 99AGG3 | 118GB, M.2 80mm PCIe 3 x4, Optane Media | 17939527 | 88 | Y | Y
Intel / Solidigm | Gen4 PCIE / U.2 | Gen4 U.2 | Storage | Alder Stream (P5800x) | SSDPF21Q016TB01 / 99A6PV | Alderstream Optane SSD (2.5in PCIe x4, 3DXP) 1.6TB | 18060893 | 10 | Y | Y
Intel / Solidigm | Gen4 PCIE / U.2 | Gen4 U.2 | Storage | Alder Stream (P5800x) | SSDPF21Q400GB01 / 99A6PN | Alderstream Optane SSD (2.5in PCIe x4, 3DXP) 400GB | 17963041 3500044631 3500052983 | 90 | Y[17] | Y
|  | Gen4 U.2 |  |  | SSDPF21Q400GA01 / 99APGX
Intel | IO debug |  | Test Card |  | DK-DEV-AGI027RES / 99ACP9 | AGIB027R29A1E2VR0, Intel® Agilex™ I-Series FPGA Development Kit/PAC Card Order | 18267260 | 1
Intel / Solidigm | Gen4 PCIE / U.2 | Gen4 U.2 | Storage | Arbordale Plus (P5510) | 99A5DP | ARBORDALE PLUS R SE (3.84TB, 2.5in PCIe 4.0 x4, 3D4, TLC) Generic Single Pack PF2KX038TZ01 | 17963041 3500044631 3500052983 | 88 | Y | Y
LSI | Gen4 PCIE |  | RAID/HBA |  | 9580-8i8e | 05-50076-00 (9580-8i8e, SAS 12GB+PCIe, 8 Int/ 8 Ext ports, SAS3916) | 3002098259 | 3 | Y | Y
Mellanox | Gen3 PCIE |  | Network/Interconnect |  | MCX354A-FCCT | [ConnectX-3] Pro VPI Adapter Card FDR InfiniBand and 40/56GbE Dual-Port QSFP | 3002096834 | 3 | Y | Y
Mellanox | Gen3 PCIE |  | Network/Interconnect |  | MCX4121A-XCAT | [ConnectX-4] Lx EN NIC, 10GbE Dual-Port SFP28 PCIe 3.0 x8 | 3002096834 | 5 | Y | Y
Mellanox | Gen3 PCIE / OCP | MLNX CX5 OCP | Network/Interconnect |  | MCX562A-ACAB | [ConnectX-5] EN, 1/10/25GbE, dual-port, SFP28, PCIe3.0 x16, OCPv3, | 3002096834 | 5 | Y | Y
Mellanox | Gen4 PCIE | MLNX CX5 | Network/Interconnect |  | MCX516A-CDAT | [ConnectX-5] EN, 100GbE, dual-port QSFP28, PCIe4.0 x16 | 3002096834 | 18
Mellanox | Gen4 PCIE | MLNX CX5 | Network/Interconnect |  | MCX556A-EDAT | [ConnectX-5] VPI adapter card, EDR IB (100Gb/s) and 100GbE, dual-port QSFP28, PCIe4.0 x16 | 3002096834 | 14
Mellanox | Gen4 PCIE |  | Network/Interconnect |  | MCX623106AN-CDAT | [ConnectX-6] Dx HHHL dual port QSFP56, PCIe Gen 4 x16 (100, 50, 25, 10, 1 GbE speed supported) | 3002096834 3500034495 | 25 | Y | Y
Mellanox | Gen4 PCIE | MLNX CX6 | Network/Interconnect |  | MCX651105A-EDAT | [ConnectX-6] VPI adapter card, 100Gb/s (HDR100, EDR InfiniBand), single-port QSFP56, PCIe4.0 x8 | 3500034017 | 14 | Y | Y
Mellanox | Gen4 PCIE | MLNX CX6 | Network/Interconnect |  | MCX623105AN-VDAT | [ConnectX-6] Dx HHHL single port QSFP56, PCIe Gen 4 x16 (200, 100, 50, 25, 10 GbE speed supported) | 3002096834 | 14 | Y | Y
Mellanox | Gen4 PCIE / OCP | MLNX CX6 OCP | Network/Interconnect |  | MCX631432AN-ADAB | [ConnectX-6] Lx OCP 3.0, dual port SFP28, PCIe Gen 4 x8 (25, 10, 1 GbE speed supported) | 3002096834 | 9 | Y | Y
Mellanox | Gen5 PCIE | MLNX CX7 | Network/Interconnect |  | MCX75310AAS-NEAT | [ConnectX-7] NDR single port, OSFP, PCIe Gen5x16, HHHL | 3002103032 3500034519 | 19 | Y | Y
Mellanox | Gen5 PCIE | MLNX CX7 | Network/Interconnect |  | MCX75310AAS-HEAT | [ConnectX-7] NDR200 single port, OSFP, PCIe Gen5x16, HHHL | 3500057466 3500058052 | 19 | Y | Y
Mellanox | Gen5 PCIE |  | Test Card |  | MQM9700-NS2F | Switch, 64 NDR ports, 32 OSFP ports, Managed, P2C airflow | 3500037676 3500044709 | 1 | Y
Microchip | Gen4 PCIE |  | RAID/HBA |  | 3258UPC16iXS | Adaptec® SmartRAID 3200 Series | 3500033935 | 2 | Y | Y
Montage | Gen5 PCIE | CA64 (x8) | CXL MEM |  | M88MX585REV | Montage CXL MEM SVB | 3500055173 | 2 | Y | Y
NationZ | IO debug |  | TPM |  | Z32H330TC-SPIDCARD- | NationZ TPM2.0 Module |  | 8 | Y
[5 empty] | 751 |  |  |  | Y | Y
Nuvoton | IO debug |  | TPM |  | 980521531-003 | Nuvoton TPM2.0 Module | 3500033674 | 8 | Y | Y
NVIDIA | Gen4 PCIE |  | Discrete Graphics |  | P1001 SKU 200/NVPN: NVA100TCGPU80NC | Tensor Core GPU, PCIe Gen4 x16, Passive PCIe - 80GB | 3500057057 | 3 | Y
Qlogic | Gen3 PCIE |  | Network/Interconnect |  | QLE2690-SR-SP | Single channel 16Gb FC HBA - LC Multi-mode Optic | 3002099988 | 2 | Y | Y
Qlogic | Gen4 PCIE |  | Network/Interconnect |  | QLE2772-SR-SP | Dual Channel, Gen 7, 32Gb FC, PCIe 4.0 | 3002099047 | 3 | Y | Y
Qlogic | Gen4 PCIE |  | Network/Interconnect |  | QLE2774-SR-SP | Quad Channel, Gen 7 32Gb FC, PCIe 4.0 | 3002099988 | 3 | Y | Y
Samsung | Gen4 PCIE |  | Storage |  | MZPLJ1T6HBJR-00007 | Samsung SSD PM1735 (1.6TB, NVMe, HHHL) | 3500033936 3500043709 | 18 | Y | Y
Samsung | Gen4 PCIE / U.2 | Gen4 U.2 | Storage |  | MZWLR7T6HALA-00007 | Samsung SSD PM1733 (7680GB, NVMe, 2.5 Inch) Gen4 X4/dual Port X2 | Intel transfer material | 75 | Y | Y
Samsung | Gen4 PCIE / U.2 | Gen4 U.2 | Storage |  | MZQL27T6HBLA-00A07 | Samsung SSD PM9A3 (7680GB, NVMe, 2.5 Inch) Gen4 X4/Single Port | Intel transfer material | 75 | Y | Y
Samsung | Gen4 PCIE / U.2 | Gen4 U.2 | Storage |  | MZWLR1T9HBJR-00007 | Samsung SSD PM1733 (1920GB, NVMe, 2.5 Inch) Gen4 X4/dual Port X2 | 3500034016 3500035102 3500035687 | 50 | Y | Y
Samsung | Gen5 PCIE / U.2 | Gen5 U.2 | Storage |  | MZWLO1T9HCJR-00B5C | PCIe Gen5x4 / NVMe, PM1743 w/ Elan controller, 2 TB | 3500057042 | 78 | Y | Y
Samsung | Gen5 PCIE / U.2 | Gen5 U.2 | Storage |  | MZWLO7T6HBLA-00B5C | PCIe Gen5x4 / NVMe, PM1743 w/ Elan controller, 8 TB | 3500057042 | 12 | Y
Toshiba/Kioxia | Gen4 PCIE / U.2 | Gen4 U.2 | Storage |  | KCM6XVUL1T60 | PCIe Gen4x4 / NVMe SSD, 2.5" U.3 1.6TB PCIe 3 DWPD SSD | 3500035111 3500035683 3500035316 3500035315 | 70 | Y | Y
Xilinx | Gen4 PCIE |  | FPGA |  | A-U280-A32G-DEV-G | Alveo U280 Data Center Accelerator Card, PCIe Gen4 x8 | 3500046619 | 2

## DIMM Inventory
Customs Date | REF | Tracking# | PO# | Module | QTY | Status | Config File Id | PN# | SKU | Status | In Stock
2022-12-30 | 100092070 | FedEx:609497804900 | 1305386880 | SK Hynix HMCG84AGBQA191N 32GB 1Rx4 PC5-5600B-PF0-1010-XT | 64 | In Stock | RF32 (16Gb 1R X4) (9x4) | M80445-001 | DDR5 5600 1Rx4 32GB RDIMM SK HYNIX | DIMM On Hand |  | DIMM Defined
|  |  |  | SK Hynix HMCG84AGBRA192N RDIMM 5600 1Rx4 32GB | 100 | In Stock | RC32 (16Gb 1R X4) | M80445-001 | DDR5 5600 1Rx4 32GB RDIMM SK HYNIX | Row Labels | Sum of QTY | Row Labels | Sum of DIMM QTY
2022-12-30 | 100092061 | FedEx:609497804965 | 1305387781 | SK Hynix HMCG78AGBRA191N 16GB 1Rx8 PC5-5600B-RD0-1010-XT | 41 | In Stock | RD16 (16Gb 1R x8) | M80323-001 | DDR5 5600 1Rx8 16GB RDIMM SK HYNIX | RA64 (16Gb 2R X4) | 508 | RA64 | 224
2022-12-19 | 100091795 | FedEx:609497799491 | 1305381207 | Samsung DIMM M321R8GA0BB0-CWMAH 2Rx4 5600MBPS 64GB | 96 | In Stock | RA64 (16Gb 2R X4) | M90109-001 | DDR5 5600 2Rx4 64GB RDIMM SAMSUNG | RC32 (16Gb 1R X4) | 134 | RC32 | 148
2022-12-30 | 100092061 | FedEx:609497804965 | 1305387781 | Samsung M321R8GA0BB0-CWMAH 64G 2Rx4 | 20 | In Stock | RA64 (16Gb 2R X4) | M90109-001 | DDR5 5600 2Rx4 64GB RDIMM SAMSUNG | RD16 (16Gb 1R x8) | 41 | RE32 | 104
2022-12-28 | 100092021 | FedEx:609497803877 | 1305385783 | Samsung M321R8GA0BB0-CWMAH 64G 2Rx4 | 88 | In Stock | RA64 (16Gb 2R X4) | M90109-001 | DDR5 5600 2Rx4 64GB RDIMM SAMSUNG | RE32 (16Gb 2R X8) | 90 | Grand Total | 476
2022-12-30 | 100092061 | FedEx:609497804965 | 1305387781 | SK Hynix HMCG94AGBRA179N 64GB 2Rx4 5600MBPS | 40 | In Stock | RA64 (16Gb 2R X4) | M80833-001 | DDR5 5600 2Rx4 64GB RDIMM SK HYNIX | RF32 (16Gb 1R X4) (9x4) | 64
2022-12-19 | 100091790 | FedEx:609497797385 | 1305377105/4502356077 | SK Hynix HMCG94AGBRA179N 64GB 2Rx4 5600MBPS | 176 | In Stock | RA64 (16Gb 2R X4) | M80833-001 | DDR5 5600 2Rx4 64GB RDIMM SK HYNIX | RB64 (16Gb 2R X4) | 20
2022-12-30 | 100092070 | FedEx:609497804900 | 1305386880 | SK Hynix HMCG88AGBRA191N 32GB 2Rx8 PC5-5600B-RE0-1010-XT | 32 | In Stock | RE32 (16Gb 2R X8) | M80836-001 | DDR5 5600 2Rx8 32GB RDIMM SK HYNIX | RD24 (24Gb 1R x8) | 24 | Row Labels | Count of DIMM QTY
2023-01-05 | 100092115 | FedEx:609497808570 | 1305391754 | Samsung DIMM M321R4GA3BB0-CWMYH 32GB 2Rx8 PC5-5600B-RE0-1010-XT | 18 | In Stock | RE32 (16Gb 2R X8) | M88794-001 | DDR5 5600 2Rx8 32GB RDIMM SAMSUNG | Grand Total | 881 | RA64 | 28
2023-01-05 | 100092115 | FedEx:609497808570 | 1305391754 | Samsung DIMM M321R4GA0BB0-CWMXH 32GB 1Rx4 PC5-5600B-RC0-1010-XT | 34 | In Stock | RC32 (16Gb 1R X4) | M87127-001 | DDR5 5600 1Rx4 32GB RDIMM SAMSUNG |  |  | RC32 | 23
2023-01-05 | 100092117 | FedEx:609497808515 | 1305391728 | Samsung M321R4GA3BB0-CWMYH 5600 32GB 2Rx8 | 24 | In Stock | RE32 (16Gb 2R X8) | M88794-001 | DDR5 5600 2Rx8 32GB RDIMM SK SAMSUNG |  |  | RE32 | 13 | 11 | -2
|  | FedEx:609497814668 P625 |  | SK Hynix HMCG94AGBRA184N 2Rx4 5600MBPS 64GB | 22 | In Stock | RA64 (16Gb 2R X4) | M80833-001 | DDR5 5600 2Rx4 64GB RDIMM SK HYNIX |  |  | Grand Total | 64
|  | FedEx:609497814668 P625 |  | SK Hynix HMCG94AGBRA182N 2Rx4 5600MBPS 64GB | 2 | In Stock | RA64 (16Gb 2R X4) | M80833-001 | DDR5 5600 2Rx4 64GB RDIMM SK HYNIX
|  |  |  | SK Hynix HMCG94AGBQA182N 5600 64GB 2Rx4 | 20 | In Stock | RB64 (16Gb 2R X4) | M80833-002 | DDR5 5600 2Rx4 (9x4) 64GB RDIMM SK HYNIX
|  |  |  | SK Hynix HMCG84AGBRA192N 5600 32GB 1Rx4 | 24 | In Stock | RD24 (24Gb 1R x8) | M87127-001 | DDR5 5600 1Rx4 32GB RDIMM SK HYNIX
|  | 628564918548 P223 | 1305408425 | Sk Hynix HMCG88AGBRA191N 32GB 2Rx8 PC5-5600B-RE0-1010-XT | 16 | In Stock | RE32 (16Gb 2R X8) | M80836-001 | DDR5 5600 2Rx8 32GB RDIMM SK HYNIX
|  |  | 1305409473 | Samsung DIMM DDR5 2Rx4 5600B 64GB M321R8GA0BB0-CWMQH | 64 | In Stock | RA64 (16Gb 2R X4) | M90109-001 | DDR5 5600 2Rx4 64GB RDIMM SAMSUNG

## Chassis Inventory
|  |  |  | Customs Clearance |  |  |  | Received |  |  |  |  | Next Shipment
Item Name | PN# | Total | Received QTY |  |  |  |  | 2023-01-04 | 2023-01-05 | 2023-01-09 | 2023-01-18 | 2023-01-19
AVC 4U CC | M36063-001 | 10 | 10 | [9 empty] | 20x WW02.5
Chassis - AVC POK | M36031-001 | 109 | 30 | [5 empty] | 25 |  | 24 | 30 | 25x (1st) + 54x (2nd) WW02.5
Motherboard for AVC POK | M35124-001 | 10 | 10 | [9 empty] | 25x WW02.5
Motherboard for BNC POK | M52902-001 | 55 | 10 |  |  |  |  | 10 | 35 |  |  |  | 10x WW08
Chassis - BNC POK | M46272-004 | 20 | 10 | [6 empty] | 10 |  |  | 18x WW07
BNC 4U CC | M52740-001 | 20 | [6 empty] | 20 |  |  |  | 1x WW09
Motherboard for AVC POK | M23789-200 | 3 | 3
Chassis Defined
|  |  |  | Row Labels | Sum of Chassis QTY
|  |  |  | CC | 20
|  |  |  | POK | 28
|  |  |  | Grand Total | 48
|  | On Hand | Used | Damage | Validation | Debug | Good
| POK | 37 | 31 | 2 | 1 | 1 | 2 | [6 empty] | AVC Board | 板子的问题描述 | 是否可以修复 | Location | Action
| CC | 30 | 24 |  |  | 1 | 5 | [6 empty] | 1.Zhang Xiong POK BB | need to debug(code-0.3) | No obvious appearance problems | Row 5 倒数第三个桌子 | debug
[16 empty] | Checking by rework - 2/13 | 板子POK在一起，无CPU，借了DIMM
[14 empty] | 2.Zhu Yuanyuan POK BB | CPU0 Pin is damaged | No
[14 empty] | 3.Zhang Yan POK BB | no power | Repaired （To be verified） Checking by rework, cannot power on - 2/13 多处短路 2/14 确定无法修复 | Rework Lab | damage 2/17
[14 empty] | 4.Zhang Yan POK BB | no power | Recovered （To be verified） | LOM damage board recovered, Rework Lab | validate--> Validated Good
[14 empty] | 5.Zhang Xiong CC BB | need to debug(code-0.3) | No obvious appearance problems | Row 5 倒数第二个桌子 | debug
板子机箱在一起
[14 empty] | 6. Zhang Yan CC BB | Slow fan speed | CPU verification required | Row 3 shelf, 板子机箱在一起 | debug

## Purchase
品名 | 规格(直径) | 数量 | Status | Delivered to
胜为电脑理线带 魔术贴桌面收纳固定整理免打孔 绕线器数据线网线电源线扎带自粘式10 |  | 30
得力(deli)30mm*3m纳米强力无痕魔力胶带 透明家用车用无痕双面胶 33601 可重复使用 |  | 30
佳能 Glad 密封袋特大号10个 食品袋 收纳衣物整理袋 密实袋 HP638C | https://item.jd.com/100024534638.html | 10 boxes (10pcs per box) | Received 100pcs | Lin, Wenyan
麦锐欧 防静电自封袋 硬盘包装袋 电子器件主板屏蔽自封袋 双层 100个/包 13*18cm | https://i-item.jd.com/100032680447.html#crumb-wrap | 5 boxes (100pcs per box) | Received 500pcs | Lin, Wenyan
绿联（UGREEN）包线管 | 20mm | 25 PCS | Received 25pcs | Lin, Wenyan
绿联（UGREEN）包线管 | 40mm | 112 PCS | Received 164pcs | Guo, Linlin
绿联（UGREEN）包线管 | 60mm | 26 PCS | N/A
HDMI to VGA cables | https://item.jd.com/100031846590.html#crumb-wrap | 10 | Received 10pcs | Lin, Wenyan
Power cord P002-002 | https://item.jd.com/10037565763973.html#crumb-wrap | 420
heatsink锡膏
Printer label 9MM black word in yellow ground |  | 30 | Received 22pcs | Lin, Wenyan
Sinmark A4 network cable labeling |  | 5 | Received 5pcs | Lin, Wenyan
PO 3500082711 | PO 3500084478
机器吊牌 |  | 500
扭力扳手的刀头 | https://item.jd.com/10065888110412.html#crumb-wrap | 5
Air blowing ball | https://item.jd.com/1275780.html | 3

## Open Lab Layout
HELP! | Open Lab SUT MAP
ROW | Entrance
1 | Node/Rack | R14 | R13 | R12 | R11 | R10 | R09 | R08 | R07 | R06 | R05 | R04 | R03 | R02 | R01
| s04 | zz14l07001s1403 | zz14l07001s1303 | zz14l07001s1203 | zz14l07001s1103 | zz14l07001s1003 | zz14l07001s0903 | zz14l07001s0804 | zz14l07001s0704 | zz14l07001s0603 | zz14l07001s0503 | zz14l07001s0404 | zz14l07001s0304 | zz14l07001s0203 | zz14l07001s0103
| s03 | zz14l07001s1402 | zz14l07001s1302 | zz14l07001s1202 | zz14l07001s1102 | zz14l07001s1002 | zz14l07001s0902 | zz14l07001s0803 | zz14l07001s0703 | zz14l07001s0602 | zz14l07001s0502 | zz14l07001s0403 | zz14l07001s0303 | zz14l07001s0202 | zz14l07001s0102
| s02 | zz14l07001s1401 | zz14l07001s1301 | zz14l07001s1201 | zz14l07001s1101 | zz14l07001s1001 | zz14l07001s0901 | zz14l07001s0802 | zz14l07001s0702 | zz14l07001s0601 | zz14l07001s0501 | zz14l07001s0402 | zz14l07001s0302 | zz14l07001s0201 | zz14l07001s0101
| s01 | [6 empty] | zz14l07001s0801 | zz14l07001s0701 |  |  | zz14l07001s0401 | zz14l07001s0301
2 | Node/Rack | [6 empty] | R08 | R07 | R06 | R05 | R04 | R03 | R02 | R01
| s05 | [6 empty] | zz14l07002s0805 | zz14l07002s0705 | zz14l07002s0605 | zz14l07002s0505 | zz14l07002s0405 | zz14l07002s0305 | zz14l07002s0205 | zz14l07002s0105
| s04 | [6 empty] | zz14l07002s0804 | zz14l07002s0704 | zz14l07002s0604 | zz14l07002s0504 | zz14l07002s0404 | zz14l07002s0304 | zz14l07002s0204 | zz14l07002s0104
| s03 | [6 empty] | zz14l07002s0803 | zz14l07002s0703 | zz14l07002s0603 | zz14l07002s0503 | zz14l07002s0403 | zz14l07002s0303 | zz14l07002s0203 | zz14l07002s0103
| s02 | [6 empty] | zz14l07002s0802 | zz14l07002s0702 | zz14l07002s0602 | zz14l07002s0502 | zz14l07002s0402 | zz14l07002s0302 | zz14l07002s0202 | zz14l07002s0102
| s01 | [6 empty] | zz14l07002s0801 | zz14l07002s0701 | zz14l07002s0601 | zz14l07002s0501 | zz14l07002s0401 | zz14l07002s0301 | zz14l07002s0201 | zz14l07002s0101
3 | Node/Rack |  | R13 | R12 | R11 | R10 | R09 | R08 | R07 | R06 | R05 | R04 | R03 | R02 | R01
| s05 |  | zz14l07003s1305 | zz14l07003s1205 | zz14l07003s1105 | zz14l07003s1005 | zz14l07003s0905 | zz14l07003s0805 | zz14l07003s0705 | zz14l07003s0605 | zz14l07003s0505 | zz14l07003s0405 | zz14l07003s0305 | zz14l07003s0205 | zz14l07003s0105
| s04 |  | zz14l07003s1304 | zz14l07003s1204 | zz14l07003s1104 | zz14l07003s1004 | zz14l07003s0904 | zz14l07003s0804 | zz14l07003s0704 | zz14l07003s0604 | zz14l07003s0504 | zz14l07003s0404 | zz14l07003s0304 | zz14l07003s0204 | zz14l07003s0104
| s03 |  | zz14l07003s1303 | zz14l07003s1203 | zz14l07003s1103 | zz14l07003s1003 | zz14l07003s0903 | zz14l07003s0803 | zz14l07003s0703 | zz14l07003s0603 | zz14l07003s0503 | zz14l07003s0403 | zz14l07003s0303 | zz14l07003s0203 | zz14l07003s0103
| s02 |  | zz14l07003s1302 | zz14l07003s1202 | zz14l07003s1102 | zz14l07003s1002 | zz14l07003s0902 | zz14l07003s0802 | zz14l07003s0702 | zz14l07003s0602 | zz14l07003s0502 | zz14l07003s0402 | zz14l07003s0302 | zz14l07003s0202 | zz14l07003s0102
| s01 |  | zz14l07003s1301 | zz14l07003s1201 | zz14l07003s1101 | zz14l07003s1001 | zz14l07003s0901 | zz14l07003s0801 | zz14l07003s0701 | zz14l07003s0601 | zz14l07003s0501 | zz14l07003s0401 | zz14l07003s0301 | zz14l07003s0201 | zz14l07003s0101
Open Lab
|  | B01 |  | B02 |  | B03 |  | B04 |  | B05 |  | B06 |  | B07
[6 empty] | empty |  | empty |  | empty |  | empty |  | empty
[8 empty] | R0062 | R0063 | R0064 | R0065 | R0066 | R0067 | R0068 | R0069
[8 empty] | empty |  | empty | empty | empty |  | empty | empty
|  |  | R0027 | R0028 | R0029 | R0030 | R0031 | R0032 | R0033 | R0034 | R0035 | R0036 | R0037 | R0038 | R0039
|  |  | R0027 | R0028 | R0029 | R0030 | R0031 | R0032 | R0033 | R0034 | empty | empty | empty | empty | empty

## BNC Shipment
Sample Description | 2022 WW46 | 2022 WW47 | 2022 WW48 | 2022 WW49 | 2022 WW50 | 2022 WW51 | 2022 WW52 | 2022 WW53 | 2023 WW1 | 2023 WW2 | 2023 WW3 | 2023 WW4 | 2023 WW5 | 2023 WW6 | 2023 WW7 | 2023 WW8 | 2023 WW9 | 2023 WW10 | 2023 WW11 | 2023 WW12 | 2023 WW13 | 2023 WW14 | 2023 WW15 | 2023 WW16 | 2023 WW17 | 2023 WW18 | 2023 WW19 | 2023 WW20 | 2023 WW21 | 2023 WW22 | 2023 WW23 | 2023 WW24
BNC 4S POK | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
BNC 4U CC | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 49 | 55 | 55 | 55 | 75 | 78 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88
BNC 8S POK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
BNC Modular Board | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 14 | 44 | 44 | 44 | 46 | 47 | 47 | 47 | 47 | 47 | 57 | 57 | 62 | 62
BNC POK | 10 | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 38 | 48 | 48 | 48 | 66 | 66 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
BNC RP Board | 0 | 10 | 10 | 10 | 10 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 65 | 80 | 80 | 90 | 100 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110 | 110

## Transformed Data
IMPORTANT DETAIL
In order to insert the PivotTable you selected, we had to organize your data in columns with a single header row.
| Field1 | Field2
| QDF | Chassis
| Q2TJ | POK
| Q2V4 | CC
| Q2TK | CC
| Q2TK | CC
| Q2TM | CC
| Q2TK | POK
| Q2V4 | POK
| Q2U2 | POK
| Q2V4 | POK
| Q2V4 | POK
| Q2TK | POK
| Q2TJ | CC
| Q2TJ | CC
| Q2TK | CC
| Q2U2 | POK
| Q2TK | POK
| Q2V4 | POK
| Q2V4 | POK
| Q2U2 | POK
| Q2U4 | POK
| Q2TK | POK
| Q2TK | POK
| Q2TH | POK
| Q2U4 | POK
| Q2TH | POK

## Sheet1
Description | Count of Description
HSIO full IO cfg | 2
MEM CfgX + 1x 3rd party AIC + 2x Storage | 2
MEM CfgX + 1x Intel AIC + 0x Storage | 2
MEM CfgX + 1x Intel AIC + 2x Storage | 5
MEM CfgX + 1x RPB + 1x Storage | 3
MEM CfgX + 2x 3rd party AIC + 2x Storage | 1
MEM CfgX + 2x Intel AIC + 0x Storage | 10
MEM CfgX + 2x Intel AIC + 2x Storage | 5
MEM CfgX + 6x MIX AIC + 8x Storage | 2
MEM CfgX only | 32
(blank)
Grand Total | 64